## Slide 1: Historic Preservation Project (CPA Funded) Phase Summary
Historic & Cultural Resources Working Group
A Subgroup of Arlington’s Master Plan Implementation Committee

## Slide 2: Project Breakdown (Total Project Cost: $115,000)
Project Phase | Funding | Duration
Phase 1: Inventory Update A | $15,000 – CPA $15,000 – MHC Survey & Planning Grant | 5.17 – 7.18
Phase 2: Survey Master Plan | $25,000 – CPA | 35 Weeks
Phase 3: Inventory Update B | $30,000 – CPA | 20 Weeks
Phase 4: Historic Structure Report | $30,000 – CPA | 16 Weeks

## Slide 3: Phase 1: Inventory Update A
The objective, cost, timeline, RFP scope, and other key components of Phase 1 were established by the Massachusetts Historical Commission as part of the Survey & Planning Grant Program.
Objective: Add 135 new (i.e., currently undocumented) properties to the Inventory Of Historically Or Architecturally Significant Properties In The Town Of Arlington ($220 per record)
Budget: $30,000 (CPA/S&P Grant) (The Town was awarded $15,000 from the grant program. This award will be used to reimburse half of the cost of Phase 1.)
Timeline: May 2017 – July 2018
The RFP is just for Phase 1.

## Slide 4: Phase 2: Survey Master Plan
Objective: Develop a survey master plan, which will include an action plan for identifying and including currently undocumented resources in the inventory, and for identifying and documenting threatened historical resources.
Budget: $25,000 (CPA)
Duration: 35 Weeks (Specific Timeline TBD)

## Slide 5: Phase 3: Inventory Update B
Objective: Correct current inventory records that are inaccurate.
Budget: $30,000 (CPA) ($220 per record)
Duration: 20 Weeks (Specific Timeline TBD)

## Slide 6: Phase 4: Historic Structure Report
Objective: Create an historic structure report for the Arlington High School building. The report will include in-depth historical research, descriptions of existing conditions, and preservation recommendations.
Budget: $30,000 (CPA)
Duration: 16 Weeks (Specific Timeline TBD)